{"text_format":"2","workbook":"xls","n_sheets":4,"sheets":["水試一號","水試二號","海安號","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"水試一號","index":0,"n_rows":26,"n_cols":7,"rows_kept":26,"cut":false,"hidden":false,"merged":[[15,6,16,6],[15,4,16,4],[15,5,16,5],[25,0,25,2],[0,0,0,6],[1,5,2,5],[1,6,2,6],[1,3,2,3],[1,0,2,0],[1,1,1,2],[1,4,2,4]],"flags":["formulas_cached_only"]}
["行政院農業委員會水產試驗所水試一號試驗船104年度計畫航次船期表"]
["月別","預定船期",null,"天數","單 位","執行人","執行計畫名稱"]
[null,"起日","迄日"]
[1,20,31,12,"海洋漁業組","陳郁凱","台灣周邊海域漁場環境監測"]
[2,5,9,5,"海洋漁業組","王友慈","鯖鰺魚類幼生成長模式之研究(I)－白腹鯖與花腹鯖的日成長模式估算"]
[2,18,23,null,null,null,"春節連假"]
[3,5,9,5,"海洋漁業組","王友慈","鯖鰺魚類幼生成長模式之研究(I)－白腹鯖與花腹鯖的日成長模式估算"]
[4,9,13,5,"海洋漁業組","王友慈","鯖鰺魚類幼生成長模式之研究(I)－白腹鯖與花腹鯖的日成長模式估算"]
[4,15,26,12,"海洋漁業組","陳郁凱","台灣周邊海域漁場環境監測"]
[5,7,11,5,"海洋漁業組","王友慈","鯖鰺魚類幼生成長模式之研究(I)－白腹鯖與花腹鯖的日成長模式估算"]
[5,12,18,7,null,"王凱毅","台灣北部海域劍尖槍鎖管資源監測與評估研究"]
[6,16,22,7,null,"王凱毅","台灣北部海域劍尖槍鎖管資源監測與評估研究"]
[6,22,6,null,"海洋漁業組","船務室","6組救生筏檢驗作業"]
[7,1,12,12,"海洋漁業組","陳郁凱","台灣周邊海域漁場環境監測"]
[7,13,19,7,null,"王凱毅","台灣北部海域劍尖槍鎖管資源監測與評估研究"]
[7,20,null,null,"海洋漁業組","船務室","歲  修"]
[8,null,31]
[9,8,14,7,null,"王凱毅","台灣北部海域劍尖槍鎖管資源監測與評估研究"]
[9,16,21,6,"海洋漁業組","王友慈","台灣沿海日本鰻苗資源調查研究"]
[10,1,12,12,"海洋漁業組","陳郁凱","台灣周邊海域漁場環境監測"]
[10,6,12,7,null,"王凱毅","台灣北部海域劍尖槍鎖管資源監測與評估研究"]
[10,14,19,6,"海洋漁業組","王友慈","台灣沿海日本鰻苗資源調查研究"]
[11,11,16,6,"海洋漁業組","王友慈","台灣沿海日本鰻苗資源調查研究"]
[12,9,14,6,"海洋漁業組","王友慈","台灣沿海日本鰻苗資源調查研究"]
[]
["預定出海日數",null,null,127]

{"sheet":"水試二號","index":1,"n_rows":29,"n_cols":7,"rows_kept":29,"cut":false,"hidden":false,"merged":[[28,0,28,2],[0,0,0,6],[1,0,2,0],[1,1,1,2],[1,3,2,3],[1,4,2,4],[1,5,2,5],[1,6,2,6]],"flags":["formulas_cached_only"]}
["行政院農業委員會水產試驗所水試二號試驗船104年度計畫預定航次船期表"]
["月別","預定船期",null,"天數","單位","執行人","執行計畫名稱"]
[null,"起日","迄日"]
[2,18,23,null,null,null,"春節連假"]
[3,9,13,5,"沿近海資源研究中心","翁進興","台灣近海鰆魚漁業資源研究"]
[3,16,20,5,"沿近海資源研究中心","楊清閔","黃鰭鮪箱網養殖生產技術之建構"]
[3,25,27,3,"沿近海資源研究中心","何珈欣","台灣西南海域底棲魚蟹類資源時空變動與永續利用之研究-Ⅵ"]
[5,4,8,5,"沿近海資源研究中心","翁進興","台灣近海鰆魚漁業資源研究"]
[5,12,15,4,"沿近海資源研究中心","頼繼昌","氣候變遷對臺灣西南海域主要經濟魚種資源與漁場影響研究"]
[5,25,29,5,"沿近海資源研究中心","楊清閔","黃鰭鮪箱網養殖生產技術之建構"]
[6,9,12,4,"沿近海資源研究中心","葉信明","台灣西南海域白帶魚屬魚類之漁業資源及生態調查"]
[6,23,25,3,"沿近海資源研究中心","何珈欣","台灣西南海域底棲魚蟹類資源時空變動與永續利用之研究-Ⅵ"]
[7,6,9,4,"沿近海資源研究中心","葉信明","台灣西南海域白帶魚屬魚類之漁業資源及生態調查"]
[7,13,17,5,"沿近海資源研究中心","翁進興","台灣近海鰆魚漁業資源研究"]
[7,27,31,5,"沿近海資源研究中心","楊清閔","黃鰭鮪箱網養殖生產技術之建構"]
[8,4,7,4,"沿近海資源研究中心","葉信明","台灣西南海域白帶魚屬魚類之漁業資源及生態調查"]
[8,18,21,4,"沿近海資源研究中心","陳玟妤","台灣沿海日本鰻資源調查研究"]
[9,1,4,4,"沿近海資源研究中心","葉信明","台灣西南海域白帶魚屬魚類之漁業資源及生態調查"]
[9,8,11,4,"沿近海資源研究中心","頼繼昌","氣候變遷對臺灣西南海域主要經濟魚種資源與漁場影響研究"]
[9,14,18,5,"沿近海資源研究中心","楊清閔","黃鰭鮪箱網養殖生產技術之建構"]
[9,21,24,4,"沿近海資源研究中心","陳玟妤","台灣沿海日本鰻資源調查研究"]
[9,29,"10/1",3,"沿近海資源研究中心","何珈欣","台灣西南海域底棲魚蟹類資源時空變動與永續利用之研究-Ⅵ"]
[10,12,"16",5,"沿近海資源研究中心","翁進興","台灣近海鰆魚漁業資源研究"]
[10,21,"23",3,"沿近海資源研究中心","陳玟妤","台灣沿海日本鰻資源調查研究"]
[11,9,"13",5,"沿近海資源研究中心","楊清閔","黃鰭鮪箱網養殖生產技術之建構"]
[11,23,25,3,"沿近海資源研究中心","陳玟妤","台灣沿海日本鰻資源調查研究"]
[12,7,11,5,"沿近海資源研究中心","翁進興","台灣近海鰆魚漁業資源研究"]
[]
["預定出海日數",null,null,97]

{"sheet":"海安號","index":2,"n_rows":20,"n_cols":7,"rows_kept":20,"cut":false,"hidden":false,"merged":[[19,0,19,2],[0,0,0,6],[1,5,2,5],[1,6,2,6],[1,0,2,0],[1,1,1,2],[1,3,2,3],[1,4,2,4]],"flags":["formulas_cached_only"]}
["行政院農業委員會水產試驗所海安號104年度計畫航次船期表"]
["月別","預定船期",null,"天數","單位","執行人","執行計畫名稱"]
[null,"起日","迄日"]
[2,18,23,null,null,null,"春節連假"]
{"$rows_empty":15}
["預定出海日數",null,null,0]

{"sheet":"Sheet3","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}